MA323 Lab09 Report
Pavan Kumar A
210123043

1a)

Since E10 has 4,8,9 as predecessors,
E10 = T10 + max(E4,E8,E9)

E4 = T4 + E2 = T4 + T2 + T1

Similarly,
E8 = T8 + T3 + T1
E9 = max(E5, E6, E7) + T9

∴ E10 = T10+max(T4 + T2 + T1 ,
   max(T8 + T3 + T1,
   T9 + max(T5 + T2 + T1,
  max(T6 + T3 + T1,
  T7 + T3 + T1))))

1b,c,d)

Taking sample size, n = 10000

Using Simple Monte Carlo yields an estimated mean E10 as 18.1153

Histogram of E10 samples generated

The graph is positively skewed, and skewness measured = 1.0737, this means that the probabilities of values greater than the mean are very small.

The estimated probability = 0.0001 (1 E10 greater than 70)
The Standard deviation of the probability = 0.009

The standard deviation is very high, thus this is an unreliable method for sampling the probability.
Also if we used a different seed, the number of E10>70 might’ve been 0, this is another reason this method is unreliable.

1e)

To Estimate probability using importance method:

which in this case is (Note that X is 10-dimensional):
p(X) = prod from{j=1} to{n} { { e^{ { -T_{ij} } wideslash {%theta_{j}} } } wideslash {%theta_{j}} }
q(X) = prod from{j=1} to{n} { { e^{ { -T_{ij} } wideslash {%lambda_{j}} } } wideslash {%lambda_{j}} }
f(X) = I lbrace E_{i,10} > 70 rbrace (Indicator for when E10 > 70)
∴ {tilde %mu}_imp = {1} wideslash {n} sum from{i=1} to{n} I { lbrace E_{i,10} > 70 rbrace } prod from{j=1} to{10} frac { { func e^{ { -T_{ij} } wideslash { %theta _{j} } } } wideslash {%theta_{j}} } { { func e^{ { -T_{ij} } wideslash { %lambda _{j} } } } wideslash {%lambda _{j}} } %sigma_{imp} ^ 2 = frac {1} {n} sum from { i=1 } to { n } (h(X_i) - {tilde %mu}_imp )^2

Where I is indicator function for even E10 > 70
θj is the mean time of the i’th process
λj = κ*θj

The product calculated is the likeliness ratio(weight).

Estimated probability using Importance method=2.879x10-5
Standard Deviation = 0.00086
Estimated Sample Size = 3.2701

The sample size is too small, this is because multiplying 4 to all the means is causing too much of a distortion. Thus this sampling is unreliable.

1f,g,h)

The formula for calculating the probability will remain same, except that when j∈{3, 5, 6, 7, 8, 9}, κ=1

κ	Estimated Probability	Number of E10>70	Standard Deviation	99% Confidence Interval for probability	Estimated Sample / Size
3	3.04889x10-5	1447	0.00017206	[2.6049x10-5, 3.4927x10-5]	917.95
4	2.82657x10-5	3142	0.00014025	[2.4647x10-5, 3.1884x10-5]	327.47
5	3.38229x10-5	4793	0.00017824	[2.9224x10-5, 3.8422x10-5]	141.05

Since only the processes on critical path, I.e, {1,2,4,10}, contribute to E10, while the the rest do not contribute as much, so we do not have to increase the mean for all the Tj, that is the reason the estimated sample sizes here are greater than the value obtained in (e).

κ=5 has the smallest estimated sample size and
the 99% confidence interval of probability = [2.9224x10-5, 3.8422x10-5]